## PM Issue Tracking
PROJECT MANAGEMENT ISSUE TRACKING
COMPANY | VALTECH |  | STATUSES | STATUS TALLY | STATUSES | STATUS TALLY
DEPARTMENT | JAVA STREAM BATCH |  | NOT STARTED | 0 | LOW | 1
PROJECT NAME | SPICELAND-ONLINE HOMEMADE SPICES AND SNACKS DELIVERY SYSTEM |  | IN PROGRESS | 1 | MEDIUM | 5
|  |  | CLOSED | 9 | HIGH | 4
ISSUE NO | ISSUE DESCRIPTION | STATUS | PRIORITY | ASSIGNEE | OPEN | CLOSED | COMMENTS
1 | REGISTRATION PAGE-Additional fields inclusion | CLOSED | LOW | BHARATH H K | 2022-12-12 | 13/12/2022 | Inclusion of additional fields replaced by address field to have clear identifications.
2 | REGISTRATION PAGE-Role Validation | CLOSED | MEDIUM | BHARATH H K | 13/12/2022 | 13/12/2022 | Solving the issue of making any one of the role as mandatory.
3 | REGISTRATION PAGE-Password Encoder | CLOSED | HIGH | DIVYASHREE M D | 2022-12-12 | 14/12/2022 | BCryptPasswordEncoder is one of the password encoders used in the spring boot security module for password encoding and password decoding or validate and was one of issue in the existing project to be solved
4 | LOGIN PAGE-Authorisation | IN PROGRESS | HIGH | YESHASWINI C | 14/12/2022
6 | ADMIN DASHBOARD-Inventory Management | CLOSED | HIGH | AKSHAY KUMAR K | 14/12/2022 | 15/12/2022 | Real-time Inventory Management usage implementation
7 | ADMIN DASHBOARD-Visibility of product images in manage and update product functionality | CLOSED | MEDIUM | YESHASWINI C | 13/12/2022 | 13/12/2022 | Creation of one more extra column in the list of products to make the visibility of image.
8 | DELIVERY PERSON-Location Based Delivery | CLOSED | MEDIUM | AKSHAY KUMAR K | 2022-12-12 | 13/12/2022 | Location Based Delivery implementation based on the ordered placed location to deliver the orders for delivery-person
9 | Usage of JENKINS | CLOSED | MEDIUM | IRFAN KATARKI | 14/12/2022 | 14/12/2022
10 | Functionality of one seller selling one product to avoid duplicate entry of that product. | CLOSED | MEDIUM | DIVYASHREE M D | 15/12/2022 | 15/12/2022 | Taking the list of products and comparing the respective ID and product_name of product resulting towards solving the stated issue.
11 | DELIVERY PERSON-SMS Service | CLOSED | HIGH | AKSHAY KUMAR K | 13/12/2022 | 13/12/2022 | Twilio messaging is a third party application used to send SMS by using Spring Boot Application programatically.
12 | ADMIN DASHBOARD-Image Size Specifications | CLOSED | MEDIUM | IRFAN KATARKI | 2022-12-12 | 13/12/2022 | Validation of image size to function the limit of image upload[Less than 1M]

## PM Issue Tracking - BLANK
PROJECT MANAGEMENT ISSUE TRACKING TEMPLATE
COMPANY |  |  | STATUSES | STATUS TALLY | STATUSES | STATUS TALLY
DEPARTMENT |  |  | NOT STARTED | 0 | LOW | 0
PROJECT NAME |  |  | IN PROGRESS | 0 | MEDIUM | 0
PROJECT MANAGER |  |  | CLOSED | 0 | HIGH | 0
ISSUE NO | ISSUE DESCRIPTION | STATUS | PRIORITY | ASSIGNEE | OPEN | CLOSE | COMMENTS
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.