## Sheet1
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date
Bug | HOME-41 | 10060 | Jenkins Setup | Irfan.Katarki | 6371f1799e48f2b9a60fe021 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-12-14 12:39 | 2022-12-16 08:17
Bug | HOME-40 | 10059 | Twilio Services/Email Service | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-12-13 08:50 | 2022-12-15 12:26
Bug | HOME-39 | 10058 | LOGIN PAGE-Authorisation-Testing phase | Yeshaswini.C | 6371f179f6c85b343c06619e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Test |  | 2022-12-13 08:48 | 2022-12-16 08:18
Bug | HOME-38 | 10057 | DELIVERY PERSON-Location Based Delivery-Testing phase | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-12-13 08:47 | 2022-12-16 08:17
Bug | HOME-37 | 10056 | Password encoder for registration-Testing phase | Divyashree.MD | 6371f1798fd2d2d5f12b896e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-12-13 08:45 | 2022-12-16 08:17
Bug | HOME-36 | 10055 | REGISTRATION PAGE-Additional fields inclusion | Bharath.HK | 6371f1799960988ef6bba007 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-12-13 08:42 | 2022-12-16 08:17
Bug | HOME-35 | 10054 | LOGIN PAGE-Authorisation | Yeshaswini.C | 6371f179f6c85b343c06619e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | In Progress |  | 2022-12-13 08:38 | 2022-12-16 08:18
Bug | HOME-34 | 10053 | ADMIN DASHBOARD-Visibility of product images in manage and update product functionality | Bharath.HK | 6371f1799960988ef6bba007 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-12-13 08:33 | 2022-12-16 08:17
Bug | HOME-33 | 10052 | DELIVERY PERSON-Location Based Delivery | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-12-12 14:55 | 2022-12-15 12:27
Bug | HOME-32 | 10051 | ADMIN DASHBOARD-Image Size Specifications | Irfan.Katarki | 6371f1799e48f2b9a60fe021 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-12-12 14:49 | 2022-12-14 12:29
Bug | HOME-31 | 10050 | Password encoder for registration. | Divyashree.MD | 6371f1798fd2d2d5f12b896e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-12-12 13:38 | 2022-12-13 18:28
Bug | HOME-30 | 10049 | Home page modifications | Irfan.Katarki | 6371f1799e48f2b9a60fe021 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 09:23 | 2022-12-02 05:42
Task | HOME-28 | 10047 | Profile Update for Delivery Person | Yeshaswini.C | 6371f179f6c85b343c06619e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 09:10 | 2022-12-02 05:41
Task | HOME-27 | 10046 | Profile Update for User | Divyashree.MD | 6371f1798fd2d2d5f12b896e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 09:08 | 2022-12-02 05:41
Task | HOME-26 | 10045 | JSP Page Design for Order Tracking and Payment Gateway | Irfan.Katarki | 6371f1799e48f2b9a60fe021 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 08:54 | 2022-12-02 05:41
Task | HOME-25 | 10044 | All JSP Page Validations | Bharath.HK | 6371f1799960988ef6bba007 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 08:52 | 2022-12-02 05:41
Task | HOME-24 | 10043 | JSP Page design for Cart page | Divyashree.MD | 6371f1798fd2d2d5f12b896e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 08:49 | 2022-12-02 05:41
Task | HOME-23 | 10042 | Testing | Yeshaswini.C | 6371f179f6c85b343c06619e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 08:45 | 2022-12-02 05:41
Task | HOME-22 | 10041 | Order Tracking page | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 08:41 | 2022-12-02 05:41
Task | HOME-21 | 10040 | Payment Gateway Page | Bharath.HK | 6371f1799960988ef6bba007 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 08:29 | 2022-12-02 05:41
Task | HOME-20 | 10039 | Cart Page | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-30 08:18 | 2022-12-02 05:41
Task | HOME-19 | 10036 | Store Image to H2-Database | Yeshaswini.C | 6371f179f6c85b343c06619e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-15 07:13 | 2022-11-25 14:20
Task | HOME-18 | 10035 | Delivery Person DashBoard | Irfan.Katarki | 6371f1799e48f2b9a60fe021 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-15 06:43 | 2022-11-23 09:15
Task | HOME-17 | 10034 | Testing | Bharath.HK | 6371f1799960988ef6bba007 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-15 06:29 | 2022-11-30 08:52
Task | HOME-16 | 10033 | User DashBoard | Divyashree.MD | 6371f1798fd2d2d5f12b896e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-15 06:24 | 2022-11-23 09:15
Task | HOME-15 | 10032 | Profile Update for Admin/Seller | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-15 06:12 | 2022-11-30 09:10
Task | HOME-14 | 10031 | Manage the product added by the Seller | Divyashree.MD | 6371f1798fd2d2d5f12b896e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-15 06:04 | 2022-11-23 09:16
Task | HOME-13 | 10030 | Admin/Seller should add Products. | Yeshaswini.C | 6371f179f6c85b343c06619e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-15 05:54 | 2022-11-23 09:15
Task | HOME-11 | 10028 | Session for each user when they logged in | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-15 05:46 | 2022-11-22 07:38
Task | HOME-10 | 10027 | Develop Admin Dashboard | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-15 05:39 | 2022-11-16 06:47
Story | HOME-9 | 10026 | Sign-in page for the Entity Delivery-Person | Yeshaswini.C | 6371f179f6c85b343c06619e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-14 12:09 | 2022-11-14 12:11
Story | HOME-8 | 10025 | Sign-up page for the Entity Delivery-Person | Yeshaswini.C | 6371f179f6c85b343c06619e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-14 12:07 | 2022-11-14 12:11
Story | HOME-7 | 10024 | Boot-Strap for JSP Pages | Irfan.Katarki | 6371f1799e48f2b9a60fe021 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-14 12:06 | 2022-11-30 08:54
Story | HOME-6 | 10023 | Sign-in page for the Entity Admin/Seller | Divyashree.MD | 6371f1798fd2d2d5f12b896e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-14 12:06 | 2022-11-14 12:11
Story | HOME-5 | 10022 | Sign-up page for the Entity Admin/Seller | Divyashree.MD | 6371f1798fd2d2d5f12b896e | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-14 12:05 | 2022-11-14 12:11
Story | HOME-4 | 10021 | Sign-In page for the Entity Customer | Bharath.HK | 6371f1799960988ef6bba007 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-14 12:04 | 2022-11-14 12:11
Story | HOME-3 | 10020 | Sign-up page for the Entity Customer | Bharath.HK | 6371f1799960988ef6bba007 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-14 12:02 | 2022-11-14 12:11
Story | HOME-2 | 10019 | Testing | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-14 12:01 | 2022-11-14 12:11
Story | HOME-1 | 10018 | Initial Project Setup | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Akshay Kumar K | 6371ed2600cb2fc3f9851d78 | Medium | Done | Done | 2022-11-14 12:01 | 2022-11-14 12:11